## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Foundation As a system, we want to set up the development environment and connect to enterprise data sources so that data can be processed automatically. | MUST HAVE | No Dependency | Ayush Kumar Dubey | 3- Completed
S1 | S1 | US-002 | Data Ingestion Layer As a data engineer, I want to load raw CSV support tickets, handle missing values, and normalize text formats so that downstream processing has clean data. | MUST HAVE | Project Foundation | Revathi Reddy | 3- Completed
S2 | S2 | US-003 | Entity Extraction Engine As an analyst, I want to automatically extract Customer, Product, and Ticket entities from unstructured text to reduce manual tagging. | MUST HAVE | Data Ingestion Completion | Ayush Kumar Dubey | 3- Completed
S2 | S2 | US-004 | Graph Construction Hub We want structured triples (entity-relation-entity) stored in Neo4j so that complex relationships become queryable. | MUST HAVE | Entity Extraction Engine | Revathi Reddy | 3- Completed
S2 | S2 | US-005 | Rich Context Engineering As an architect, I want to combine demographic and issue data into a 'Rich Context' node property so that AI retrieval is more accurate. | MUST HAVE | Graph Construction Hub | Ayush Kumar Dubey | 3- Completed
S3 | S3 | US-006 | Embedding Generation As a system, I want to generate mathematical vectors for graph data using Hugging Face models so that semantic meaning is captured. | MUST HAVE | Rich Context Engineering | Ayush Kumar Dubey | 3- Completed
S3 | S3 | US-007 | Vector Indexing As a developer, I want to build a native Vector Index inside Neo4j so that we avoid external dependencies like FAISS. | MUST HAVE | Embedding Generation | Ayush Kumar Dubey | 3- Completed
S3 | S3 | US-008 | Graph RAG Pipeline As an executive, we want contextual Q&A over enterprise data using Llama-3 so that decisions are insight-driven and hallucination-free. | MUST HAVE | Vector Indexing | Revathi Reddy | 3- Completed
S4 | S4 | US-009 | Analytics Dashboard As a manager, I want a web interface with live database statistics so that I can monitor total tickets, unique customers, and product trends in real-time. | MUST HAVE | Graph RAG Pipeline | Ayush Kumar Dubey | 3- Completed
S4 | S4 | US-010 | Conversational UI As a non-technical user, I want an interactive chat interface to ask data questions in plain English so that I don't need to write Cypher queries. | MUST HAVE | Graph RAG Pipeline | Revathi Reddy | 3- Completed
S4 | S4 | US-011 | Cloud Deployment As an admin, I want the dashboard securely deployed on Streamlit Cloud with protected secrets so that remote stakeholders can access it. | SHOULD HAVE | Analytics Dashboard | Ayush Kumar Dubey & Revathi Reddy | 3- Completed
Note on F1: : ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 123 | 14 | 17 | 15 | 17 | 17 | 19 | 18 | 6 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Est (Hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9-13
US-001 | 1 | Setup Python virtual env, install dependencies, and setup project structure. | 2026-01-05 | 2026-01-06 | Ayush Kumar Dubey | Others | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Gather and analyze sample enterprise support tickets CSV data. | 2026-01-06 | 2026-01-07 | Revathi Reddy | Design | 3- Completed | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 3 | Write normalize_tickets.py to handle missing values and nulls. | 2026-01-08 | 2026-01-12 | Revathi Reddy | Coding | 3- Completed | 8 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 0
US-002 | 4 | Normalize text strings to prevent duplicate graph nodes and test output. | 2026-01-12 | 2026-01-14 | Ayush Kumar Dubey | Coding | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0
US-003 | 5 | Develop entity_extractor.py to map rows to Customer, Product, Ticket entities. | 2026-01-19 | 2026-01-21 | Ayush Kumar Dubey | Coding | 3- Completed | 10 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 6 | Configure Neo4j AuraDB credentials and establish connection. | 2026-01-21 | 2026-01-22 | Revathi Reddy | Others | 3- Completed | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
US-004 | 7 | Write graph_builder.py Cypher queries using MERGE logic. | 2026-01-22 | 2026-01-26 | Revathi Reddy | Coding | 3- Completed | 12 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0
US-005 | 8 | Implement "Rich Context" string concatenation for AI optimization. | 2026-01-26 | 2026-01-28 | Ayush Kumar Dubey | Design | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0
US-006 | 9 | Integrate Hugging Face all-MiniLM-L6-v2 for embeddings. | 2026-02-02 | 2026-02-04 | Revathi Reddy | Coding | 3- Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 10 | Script create_vector_index.py to index data natively in Neo4j. | 2026-02-04 | 2026-02-06 | Ayush Kumar Dubey | Coding | 3- Completed | 10 | 0 | 0 | 4 | 4 | 2 | 0 | 0 | 0 | 0
US-008 | 11 | Develop LangChain retrieval pipeline (rag_agent.py) with Llama-3. | 2026-02-06 | 2026-02-10 | Revathi Reddy | Coding | 3- Completed | 12 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0
US-008 | 12 | Write test_retrieval.py to debug query results and test hybrid search. | 2026-02-10 | 2026-02-11 | Ayush Kumar Dubey | Integration Test | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0
US-009 | 13 | Build app.py Streamlit layout and extract live Neo4j metrics. | 2026-02-16 | 2026-02-18 | Ayush Kumar Dubey | Design | 3- Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | 14 | Implement interactive iMessage-style chat UI and connect to RAG. | 2026-02-18 | 2026-02-20 | Revathi Reddy | Coding | 3- Completed | 12 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0
US-010 | 15 | Configure retrieval and test for hallucinations. | 2026-02-20 | 2026-02-23 | Revathi Reddy | Integration Test | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0
US-011 | 16 | Set up requirements.txt (CPU-only Torch) and Streamlit Secrets for cloud deploy. | 2026-02-23 | 2026-02-24 | Ayush Kumar Dubey | Others | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
Note on D2: : ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: : ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on K3: : ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: : ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: : ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: : ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: : ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: : ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: : ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: : ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: : ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: : ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: : ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: : ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: : ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work
Note on I3: : ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: : ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint | Day | Impediments (Discussion Topics) | Action Taken
Sprint 1 | Day 2 | Project Discussion & Preprocessing: Need a robust strategy for handling noisy enterprise data (NaNs, mismatched types) before it hits the NLP pipeline. | Discussed Pandas-based cleaning techniques with mentor; finalized an automated preprocessing script for NaN imputation and regex-based text normalization.
Sprint 1 | Day 6 | Data Cleaning: Preprocessing phase was failing to catch trailing whitespaces, creating a risk of duplicate nodes in the future graph. | Conducted a technical code review; implemented strict .strip() and .lower() algorithms in the ingestion pipeline to ensure data consistency.
Sprint 2 | Day 12 | Entity Extraction: Challenges in defining the logic to parse unstructured ticket text into clean subject-predicate-object triples. | Brainstormed extraction logic with mentor; refined entity_extractor.py to accurately map Customer, Product, and Ticket entities into a unified schema.
Sprint 2 | Day 18 | Graph Modeling: Cypher query inefficiencies causing bottlenecks and potential data duplication during graph construction. | Reviewed database architecture during stand-up; transitioned from CREATE to MERGE clauses to ensure idempotent node creation in Neo4j.
Sprint 3 | Day 25 | Embedding Extraction: Needed to finalize the vectorization strategy to capture semantic meaning rather than relying on keyword matching. | Discussed model selection; finalized integration of Hugging Face's all-MiniLM-L6-v2 for generating high-dimensional vector embeddings for the text.
Sprint 3 | Day 30 | Model Enhancement & Indexing: Neo4j vector indexing was retaining stale embeddings during iterative testing, skewing search results. | Collaborated with mentor to engineer a programmatic DROP INDEX sequence, ensuring the vector space always updates with fresh embedding extractions.
Sprint 4 | Day 40 | Context Injection: The RAG pipeline suffered from fragmented context, causing the LLM to hallucinate during hybrid search retrieval. | Discussed prompt engineering enhancements; designed the "Rich Context" concatenated string to maximize embedding density and improve semantic retrieval accuracy.
Sprint 4 | Day 45 | Deployment Bottleneck: Cloud deployment failed due to the massive 800MB+ memory footprint of the default PyTorch GPU dependencies. | Pair-programmed to refactor requirements.txt, explicitly targeting the --extra-index-url for the CPU-only Torch wheel to bypass cloud constraints.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-01-05 | 2026-01-14 | Ayush Kumar Dubey and Revathi Reddy | Implementing strict data validation rules (like .strip(), .lower()) earlier in the ingestion pipeline. | Underestimating the noisiness and missing values (NaN) of raw enterprise CSV data. | Pair-programming for core logic modules and holding daily mentor syncs. | Created a robust Pandas preprocessing protocol for NaN imputation and string normalization.
2 | Sprint 2 | 2026-01-19 | 2026-01-28 | Ayush Kumar Dubey and Revathi Reddy | Testing Cypher queries in the Neo4j browser before hardcoding them into Python scripts. | Using CREATE clauses that lead to duplicate "ghost" nodes during data ingestion. | Maintaining clear ontology design and schema mapping documentation for entities. | Transitioned to MERGE clauses for idempotent node creation and finalized the Knowledge Graph schema.
3 | Sprint 3 | 2026-02-02 | 2026-02-11 | Ayush Kumar Dubey and Revathi Reddy | Engineering the "Rich Context" strings to maximize embedding density before vectorization. | Relying on stale vector indexes in Neo4j during iterative embedding model testing. | Leveraging native Neo4j vector search instead of complex multi-database FAISS setups. | Programmed a DROP INDEX sequence and successfully implemented the hybrid Graph RAG retrieval pipeline.
4 | Sprint 4 | 2026-02-16 | 2026-02-24 | Ayush Kumar Dubey and Revathi Reddy | Reviewing cloud deployment memory constraints before finalizing standard requirements.txt. | Tracking local .env files and large .whl files in the Git version control system. | Refining the Llama-3 prompt engineering and retrieval logic. | Optimized dependencies (CPU-only PyTorch), secured Streamlit secrets, and successfully deployed the dashboard.